## CONCERN_TRACKER
Referee Concern Classification + Strategy
# | Referee | Concern (verbatim) | Classification | Strategy | Effort | Status
1 | R1 | Identification strategy unclear | CRITICAL | Add detailed section + 2 falsification | 2 wk | In progress
2 | R2 | Sample selection bias | CRITICAL | Heckman + sensitivity | 1 wk | Planned
3 | R1 | Robustness insufficient | IMPORTANT | Add 3 robustness checks | 3 d | Planned
4 | R3 | Mechanism unclear | IMPORTANT | Add channel analysis | 5 d | Planned
5 | R2 | Indonesian context | IMPORTANT | Re-write intro paragraph | 2 d | Planned
6 | R3 | Variable definition | MINOR | Update Table 1 footnotes | 2 hr | Done
7 | R1 | Citation Smith 2024 | MINOR | Add citation, verify | 1 hr | Done
8 | R2 | Typo page 5 | COSMETIC | Fix | 5 min | Done

## RESPONSE_TEMPLATE
R&R Response Letter Template
Section | Template Text
Greeting | Dear [Editor name], Thank you for the opportunity to revise our manuscript [Title]. We have carefully addressed each comment from the editor and three referees. Below is our detailed response.
Summary of major changes | Major changes in this revision: 1. [Added X identification strategy] 2. [Implemented Y robustness battery] 3. [Re-wrote Section Z with theoretical strengthening] 4. [Added N new references]
Per-concern response | Referee X, Comment Y: [Paste verbatim quote] Response: We thank the referee for this insightful comment. [Acknowledge specific point.] [Action 1] We have [done X]. See Section Y, page Z. [Action 2] We further [done X2]. [Evidence] As shown in Table N, the result [confirms / strengthens]. We believe this revision adequately addresses the concern.
Closing | We appreciate the constructive feedback and believe the revision substantially strengthens the manuscript. We look forward to your decision. Sincerely, [Authors]

## TONE_GUIDE
R&R Tone: DO and DON'T
DO checkmark | DON'T
'We thank the referee for this insightful comment.' | 'The referee is wrong.'
'We agree that this point deserves attention.' | 'This comment is irrelevant.'
'The referee makes an excellent point.' | 'We don't think this matters.'
'We have implemented [specific change], see Section X.' | 'We addressed this.' (vague)
'We respectfully disagree because [evidence].' | 'We disagree.' (defensive)
'This is a thoughtful suggestion. We have...' | 'This suggestion is not feasible.'
Always reference page/table/section specific | Generic acknowledgment

## ACCEPTANCE_PREDICTION
Acceptance Probability Predictor - KALKULATOR HIDUP
Cara pakai: ubah kolom 'Berlaku? (1/0)'. Kolom Kontribusi & Probabilitas dihitung OTOMATIS oleh formula -- tidak ada angka jadi (hardcode).
Langkah 1 - Base rate (R&R moderat = titik awal) | 30% | <- ganti kalau jurnal beda
Langkah 2 - Centang faktor yang berlaku (1=ya, 0=tidak):
Faktor | Dampak (delta) | Berlaku? (1/0) | Kontribusi (=Dampak x Berlaku)
Critical concerns fully addressed | 30% | 1
All robustness checks added | 15% | 1
Indonesian context strengthened | 10% | 0
Mechanism analysis added | 10% | 0
Major referee request NOT addressed | -30% | 0
Defensive tone in letter | -15% | 0
Vague responses | -20% | 0
Effective cover letter summary | 10% | 1
Sigma Kontribusi
Langkah 3 - Prediksi mentah = Base + Sigma Kontribusi
PREDIKSI AKHIR (dibatasi 0-100%)
Apa artinya: MEDIAN(0; mentah; 1) memilih nilai TENGAH -> otomatis memangkas hasil <0% atau >100% jadi rentang wajar (clamp).
Benchmark referensi (bukan hitungan -- pembanding hasil di atas):
Strong R&R response | 50-70%
Moderate R&R response | 30-50%
Weak R&R response | 10-25%
Major issues not addressed | < 10%